## README
Stage07 Intraday Exception Control Workbook
Stage | Stage 7 - Live-day exception board and replan deltas
Artifact | Stage07 Intraday Exception Control Workbook
Version | v1.0
Status | EXAMPLE - COMPLETED
Usage
Fill blue sheets/tables with synthetic data only.
Do not overwrite formulas or controlled vocabularies without versioning.
No raw customer banking/payment or sensitive medical details.

## Exception_Board
Incident_ID | Detected_At | Zone_ID | Route_or_Bundle_ID | Issue_Type | Severity | ETA_Risk_Min | Owner | Status | Proposed_Action | Approval_Required | Approval_Ref
INC-001 | 2026-03-04 08:05 | BE-EAST | PUB-005 | no_show | High | 35 | D-201 | In Progress | Move F-401 later and extend C-102 coverage | Y | APR-REPLAN-001
INC-002 | 2026-03-04 12:40 | BE-SOUTH | BND-007 | delay_cluster | Medium | 25 | D-201 | Monitoring | Trigger route resequence if ETA risk > 30 | N

## Replan_Deltas
Delta_ID | Supersedes_Assignment_ID | New_Worker_ID | New_Shift_Start | New_Shift_End | New_Zone_ID | New_Vehicle_ID | Reason_Code | Effective_At | Official_Status
DELTA-001 | PUB-005 | C-102 | 10:00 | 19:30 | BE-EAST | V-12 | overtime_extension | 2026-03-04 08:20 | Official
DELTA-002 | PUB-003 | F-401 | 11:00 | 17:00 | BE-SOUTH | V-17 | cross_zone_override | 2026-03-04 08:20 | Official

## Escalations
Escalation_ID | Incident_ID | Escalated_To | Escalated_At | Decision | Decision_At | Notes
ESC-001 | INC-001 | OM-01 | 2026-03-04 08:15 | Approved major replan | 2026-03-04 08:18 | Overtime + cross-zone override accepted
ESC-002 | INC-002 | S-301 | 2026-03-04 12:45 | Monitor only | 2026-03-04 12:46 | No SLA waiver yet

## LOOKUPS
Issue_Type | Reason_Code | Severity
no_show | cover_callout | Low
vehicle_issue | cross_zone_override | Medium
delay_cluster | sla_waiver | High
weather_disruption | contractor_activation | Critical
address_issue | overtime_extension | High

## Checks
Control checks
Partition | [ScheduleDateID]
Rows present
Reviewed by

## Change_Log
Change_ID | Changed_By | Changed_At | What_Changed | Why | Approved_By | Approved_At | Ticket/Case_ID